## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Select Tablets Vendors | bar: WEEK 1 F; WEEK 4 F; WEEK 7 F; WEEK 10 F
Research tablets vendors |  |  |  | 2 days | bar: WEEK 1 F; WEEK 4 F; WEEK 7 F; WEEK 10 F
Source for tablets with add ons and coupons |  |  |  | 1 day | bar: WEEK 1 F; WEEK 4 F; WEEK 7 F; WEEK 10 F
Create a software for vendors |  |  |  | 3 days
Milestone 2: Tablets installation in the North and Downtown locations
Receive tablets |  |  |  | 14 days
Schedule an electrician |  |  |  | 2 days
Insert tablets in bar areas |  |  |  | 1 day
Integrate tablets with food ordering software |  |  |  | 1 day
Connent tablets with backend |  |  |  | 2 days
Run a tablet test |  |  |  | 2 days
Finish testing period |  |  |  | 3 days
Milestone 3: Tablets Operations
Update website and menu design |  |  |  | 5 days
Asign someone to implement a survey for customer satisfations |  |  |  | 1 day
Enable GPS locations on each tablets |  |  |  | 9 days
Milestone 4: Staff training and buy ins
Schedule a second training with all staff at each locations |  |  |  | 7 days
Test run the staff training |  |  |  | 1 day
Schudule meetings with GMs to get waitstaff buy ins |  |  |  | 2 weeks
Schedule a training for the downtown locations |  |  |  | 1 hour
Train the staff to update the menu |  |  |  | 1 week
Milestone 5: Launch day |  |  |  | 4 hours
Plan a launch day |  |  |  | 4 days
Explain accomplishment to key stakeholders |  |  |  | 1 day
Launch and land the project |  |  |  | 3 days
2 days

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Select Tablets Vendors
Research tablets vendors |  | 1 day |  |  |  | H
Source for tablets with add ons and coupons |  | 2 days
Create a software for vendors |  | 2 days |  |  |  | H
Milestone 2: Tablets installation in the North and Downtown locations
Receive tablets |  | 14 day | 10 days | 12 days | 2 weeks | M
Schedule an electrician |  | 4 days | 2 days | 16 hours
Insert tablets in bar areas |  | 3 day | few hours | few days | over a week
Integrate tablets with food ordering software | Pos might take 3-4 hours to update if its not on 3.0 | 2 day | few hours | 2 days | 4 days
Connent tablets with backend |  | 2 days
Run a tablet test |  | 1 day
Finish testing period |  | 5 days
Milestone 3: Tablets Operations
Update website and menu design |  | 9 days | few days | 1 week | 2 weeks | H
Asign someone to implement a survey for customer satisfations |  | 7 days
Update menu add ons and coupons |  | 1 day
Enable GPS locations on each tablets | Training are to take place on separate days | 1 day
Milestone 4: Staff training and buy ins
Schedule a second training with all staff at each locations |  | 2 hours
Intitial training for managers |  | 4 hours
Test run the staff training |  | 1 week
Schudule meetings with GMs to get waitstaff buy ins |  | 1 hour
Schedule a training for the downtown locations |  | 1 hour
Train the staff to update the menu |  | 4 days
Milestone 5: Launch day
Plan a launch day |  | 3 days
Explain accomplishment to key stakeholders |  | 2 days
Launch and land the project |  | 2 days

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Resturant tablets- is it worth an investment? | https://plumpos.com/restaurant-technology/restaurant-tablets.html | 2021-01-12
The best way to use tablets at your resturant | https://www.business.com/articles/best-tablet-uses-restaurants/ | 2021-01-12 | There are many reasons why some restaurants are switching to tablets, including improvements to the customer experience, increased efficiency and greater profit
How to develop a successful POS implementation plan. | https://www.talech.com/blog/2020/05/07/resources-how-to-develop-a-successful-pos-system-implementation-plan/ | 2021-01-12 | Developing the right POS system implementation plan is just one step towards helping your company reach important milestones
Digital ordering systems for resturants | https://tacitcorporation.com/digital-food-ordering-system/ | 2021-01-12 | The best digital food ordering system must be conducive to the nuances of running a restaurant, kitchen, dining room, and delivery service. It must transcend what individual systems fall short in unifying kitchen and restaurant management.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Avervage ticket time | 8 minutes for appetizers and 12-15 minutes for entrees | Are customers receiving their orders during the time period indicated? | Positive reviews from the customers regarding ticket time. | FALSE
Average Table Turn Time | Bring down to average table turn time by 30mins | Are the goal been ment by bringing down the average table turn? | Improvement on customers satisfaction rates. Increase in the daily income of customers. | FALSE
Checkout Time | A checkout time of one minute or less | Are customers able to successfully checkout in one minute or less? Are the customers satisfied with the checkout time? | Customers are able to check out effortlessly without delay within one minute or less. | FALSE
Technical Issues | Less than 5% of customers to report technical issues every week | Do customers have any issues when operating the tablets? Are the issues more than 5% weekly? | 95% of customers receives their order when they use the tablet. | FALSE
Order Accuracy | Achieve 98% order accuracy | Are customers able to quickly understand and navigate through the table to place their orders without errors? Are staffs finding it hard to process the orderes? | 98% of customers who uses the tablets recives their correct order. | FALSE
Average Wait Time | Decrease customer wait time in the lobby by 10 minutes or less. | Are customers satisfied with this wait time? Has our goal been meant to reduce the wait time by 10 mins? | Guests with shorter wait times report wanting to return more often is they are being attented to on time. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
8 minutes for appetizers and 12-15 minutes for entrees | Are customers receiving their orders during the time period indicated? | Positive reviews from the customers regarding ticket time. | How long does it take for your appetizers to be served? | Multiple choice | 2-5 mins | 5 mins | 4-6 mins | 4 mins | 4-6 mins
Bring down to average table turn time by 30mins | Are the goal been ment by bringing down the average table turn? | Improvement on customers satisfaction rates. Increase in the daily income of customers. | How long do you have to wait to get a table? | Multiple choice | 20 mins | 20-25 mins | 15-17 mins | 15 mins | 22 mins
A checkout time of one minute or less | Are customers able to successfully checkout in one minute or less? Are the customers satisfied with the checkout time? | Customers are able to check out effortlessly without delay within one minute or less. | Can you checkout your order within a minute or less? | Yes or No questions (Y/N) | YES | YES | YES | YES | YES
A checkout time of one minute or less | Are customers able to successfully checkout in one minute or less? Are the customers satisfied with the checkout time? | Customers are able to check out effortlessly without delay within one minute or less. | Have you ever checked out your order for more than a min? | Yes or No questions (Y/N) | No | NO | NO | NO | NO
Less than 5% of customers to report technical issues every week | Do customers have any issues when operating the tablets? Are the issues more than 5% weekly? | 95% of customers receives their order when they use the tablet. | Have you ever encountered any difficulty operating the tablets? | yes or No questions (Y/N) | NO | YES | NO | YES | NO
Less than 5% of customers to report technical issues every week | Do customers have any issues when operating the tablets? Are the issues more than 5% weekly? | 95% of customers receives their order when they use the tablet. | On a scale of 0-5 how will you rate the functionality of the tablets | Scaled questions (0-5) | 4 | 5 | 4 | 5 | 5
Achieve 98% order accuracy | Are customers able to quickly understand and navigate through the table to place their orders without errors? Are staffs finding it hard to process the orderes? | 98% of customers who uses the tablets recives their correct order. | On a scale of 0-5 rate how easy to use in the tablet? | scaled questions (0-5) | 4 | 4 | 5 | 5 | 5
Achieve 98% order accuracy | Are customers able to quickly understand and navigate through the table to place their orders without errors? Are staffs finding it hard to process the orderes? | 98% of customers who uses the tablets recives their correct order. | Is your order always accurate when delivered to your table? | yes or No questions (Y/N) | YES | NO | YES | YES | YES
Decrease customer wait time in the lobby by 10 minutes or less. | Are customers satisfied with this wait time? Has our goal been meant to reduce the wait time by 10 mins? | Guests with shorter wait times report wanting to return more often is they are being attented to on time. | Are you satisfied with the 10 mins wait time? | Open ended question | Satisfied | very satisfied | Satisfied | Somewhat satisfied | satisfied
Decrease customer wait time in the lobby by 10 minutes or less. | Are customers satisfied with this wait time? Has our goal been meant to reduce the wait time by 10 mins? | Guests with shorter wait times report wanting to return more often is they are being attented to on time. | Have you waited for more than 10 mins, before attended to? | Yes or No questions (Y/N) | NO | YES | NO | NO | NO