## Tasks and Timeline
Sauce & Spoon Project Plan
No | Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Sourcing tablets, new software and customize it
1.1 | Generate quotes and review costs |  |  |  | 3
1.2 | test and select a custom branding package from Terrific Tablet supplier |  |  |  | 4
1.3 | Create contracts and statement of work for vendors |  |  |  | 1
1.4 | Connect the S&S marketing team with Terific Tablet for branding |  |  |  | 1
1.5 | create the menu interface for tablet | Need the menu from Carter 7 to 14 days needed |  |  | 7
2 | Install tablets, new software and test it
2.1 | Order and Recieve tablets |  |  |  | 10
2.2.1 | Schedule an electrician, Get the table wired to keep tablet charged during service. Downtown and North | need to chedule 2 half days per locations |  |  | 6
2.4 | Replace broken devices |  |  |  | 2
2.5 | Sync POS system with ordering software | Need to be POS 3.0, if not, it can take few days to the updated version |  |  | 3
2.5 | Check the quality of WiFi |  |  |  | 1
2.6 | Use two different WiFi provider |  |  |  | 1
2.7 | Define which apps and drink should be put in add-on | Need the menu from Carter 7 to 14 days needed |  |  | 3
2.8 | Define which metrics should appear in the dashboard and how |  |  |  | 2
2.9 | Test the tablets in the bar area |  |  |  | 1
3. Train management, FOH staff, and BOH staff
3.1 | Plan a team meeting with GM's to onboard them |  |  |  | 5
3.2 | Create or find tutos for Tablet software |  |  |  | 2
3.3 | Create course material for the training |  |  |  | 3
3.4 | Train some key staff members |  |  |  | 1
3.5 | Train staff to update the menu |  |  |  | 2
4. Survey for customers
4.1 | Create a post dining customer survey, define the questions to assess customer satisafction |  |  |  | 3
4.2 | Find out how we gonna hand out the survey |  |  |  | 1
5. Testing and launch plan
5.2 | Create a launch day plan : staffing, troubleshooting, etc. |  |  |  | 2
5.3 | Invite friends and family for full service |  |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 | Sourcing tablets, new software and customize it
1.1 | Generate quotes and review costs |  | 3
1.2 | select a custom branding package from Terrific Tablet supplier |  | 4
1.3 | Create contracts and statement of work for vendros
1.4 | Connect the S&S marketing team with Terific Tablet for branding
1.5 | create the menu interface for tablet | Need the menu from Carter 7 to 14 days needed | 7 | 7 | 14 | 28 | L
2 | Install tablets, new software and test it
2.1 | Order and Recieve tablets |  | 10 | 7 | 10 | 14
2.2.1 | Schedule an electrician | need to chedule 2 half days per locations, check with electricians when it suits them best, inform GM when locations nee d to close for wiring. | 4 | 4 | 6 | 10 | M
2.3 | Install the tablets in the bar area Downtown and North restaurants
2.4 | Replace broken devices | it takes one day to replace broken devices
2.5 | Sync POS system with ordering software | Need to be POS 3.0, if not, it can take few days to the updated version | 5 | 1 | 3 | 5 | L
2.5 | Check the quality of WiFi
2.6 | Use two different WiFi provider
2.7 | Define which apps and drink should be put in add-on | Need the menu from Carter 7 to 14 days needed | 7 | 7 | 14 | 28 | L
2.8 | Define which metrics should appear in the dashboard and how
2.9 | Test the tablets in the bar area |  | 0
3. Train management, FOH staff, and BOH staff
3.1 | Create course material for the training | It takes about a week to plan and creat the staff traiing | 5 | 5 | 7 | 10 | H
3.2 | Plan a team meeting with GM's to onboard them |  | 1 | 1 | 4 | 10 | H
3.3 | Train some key staff members |  | 1 | 1 | 3 | 5 | H
3.4 | Train staff to update the menu |  | 2 | 2 | 4 | 6 | H
4. Survey for customers
4.1 | Create a post dining customer survey, define the questions to assess customer satisafction
4.2 | Find out how we gonna hand out the survey
5. Testing and launch plan
5.2 | Create a launch day plan : staffing, troubleshooting, etc.
5.3 | Invite friends and family for full service

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Fluid+Company | Click Here | 2021-12-02 | Restaurants are Using Digital Menus to Gain a Competitive Advantage
PYMNTS.com | Click Here | 2021-12-02 | Restaurant Roundup: Eateries Double Down On Contact-Free Technologies

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | Average ticket time: eight minutes for appetizers and 12-15 minutes for entrees | Under eight minutes for appetizers and 12-15 minutes for entrees? | average wait time is eight minutes for appetizers and 12-15 minutes for entrees
Customer satisfaction | one-minute checkout time and ensure the checkout process is seamless and easy to navigate from a user perspective | How quickly are customers learning how to navigate the tablets? | 5% of customers have trouble using the tablet per week
Customer satisfaction | less than 5% of customers who use the tablets to report technical issues each week. | Do all the tablets work as expected? | Less than 5% of tablet errors are reported
Customer satisfaction | 98% order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order
Customer satisfaction | Lobby wait time of under 10 minutes | How many people are waiting in the lobby at a time? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times
Employee Satisfaction | 98% of waitstaff are trained on tablets | To what extent do tablets increase work performance? | Tablet error logs report a maximum of one error per shift

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time: eight minutes for appetizers and 12-15 minutes for entrees | Under eight minutes for appetizers and 12-15 minutes for entrees? | average wait time is eight minutes for appetizers and 12-15 minutes for entrees | How likely are you to return to Sauce & Spoon? | Multiple choice | Often | Sometimes | Rarely | Never
one-minute checkout time and ensure the checkout process is seamless and easy to navigate from a user perspective | How quickly are customers learning how to navigate the tablets? | 5% of customers have trouble using the tablet per week | Did you experience and technical issues while using the tablets? | Yes/No | Yes | No
less than 5% of customers who use the tablets to report technical issues each week. | Do all the tablets work as expected? | Less than 5% of tablet errors are reported | How would you describe your overall dining experience? | Open-ended | open-ended
98% order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | How accurate were your food orders? | Open-ended | open-ended
Lobby wait time of under 10 minutes | How many people are waiting in the lobby at a time? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | Did you utilize the tablets during your visit? | Yes/No | Yes | No
98% of waitstaff are trained on tablets | To what extent do tablets increase work performance? | Tablet error logs report a maximum of one error per shift | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience? | Scaled | 1 | 2 | 3 | 4 | 5
|  |  | How long do you estimate it took to place your order? | Open-ended | open-ended
|  |  | The lobby wait-time was extensive, over 10 minutes. | True/False | TRUE | FALSE
|  |  | How long was your total dining experience? | Open-ended | open-ended
|  |  | On a scale of 1-4, 1 being difficult and 4 being easy, how would you rate the tablet use? | Scaled | 1 | 2 | 3 | 4
|  |  | What part of your dining experience was enjoyable? | Open-ended | open-ended